## Project General Info
Project Name | IOP Extension Package
Project Participants | Oscar Luna
Role | Name | Initials
sponsor | Manuel Alves | MA
cost center
Project Manager | Claudia Sandigo | CS
Technical Leader | Oscar Luna | OL
Project Team member 1 | Oscar Luna | OL
Project Team member 2
Project Team member 3
Approved Requirements providers | Costumer provider
Revision History
Revision number | Date | Notes
0.1 | 2008-02-11 | First draft of PWM requirements
0.2 | 2008-02-14 | GUI requirements removed from this version. These same requirements will remain in next PWM package
0.3 | 2008-02-18 | Init requirements modified
0.4 | 2008-02-19 | Autosar version changed to version 2.1 instead 3.0

## ADC Requirement List
Control Fields | [8 empty] | Required Fields |  |  | Optional Fields Used for organization and a better understanding of Requirements |  |  |  |  | Traceability Fields | [5 empty] | Requirement check List | [7 empty] | Requirement Accomplished | Test Status
Capture Date | Capturer | Req Status | Req Rev | Rev Date | Authorize | Req Source | Req Notes | CHANGE ID | Req ID | Description / function | Other Req. Relationship | Notes on the requirement | Priority | Requirement Classification | Necessity | Assumptions | Test ID | Test Description | TS ID | TS Description | WBS ID | WBS Description | Test case associated with the requirement | The requirement can be understood by affected parties (e.g. developers, testers). | Requirement contains no TBD. | Unacceptable words and phrases are absent (e.g., adverbs, adjectives, as appropriate, at a minimum). | Requirement is at the appropriate level of detail | Requirement is within scope. | Requirement is feasible. | Requirement can be traced to its parent or driver. | Requirement Accomplished date | Test Status
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1 | ADC Initialization | [13 empty] | 1 | 1 |  | 1 | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.1 | Variable Initialization |  |  |  | Soft-High Level Drivers | [9 empty] | 1 | 1 |  | 1 | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.1.1 | Initilize as many buffers as ADC channels being available in the Adc_Cfg.c file. |  |  |  | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  | 1 | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.1.2 | Each ADC Channel shall be attached to an specific buffer to storage average results. |  |  |  | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  | 1 | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.1.3 | ADC buffers cannot be assigned twice. Storage buffers shall be assigned to a particular ADC channel to avoid lossing information. |  |  |  | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  | 1 | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.1.4 | Each ADC channel has to allocate a data buffer large enough to store the number of samples in the filter calculation.
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.1.5 | ADC Initialization function shall be invoked just once. |  |  |  | Soft-Application Functions |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.2 | HW resources | [13 empty] | 1 | 1 |  |  |  |  | 1
2008-10-24 | OL | initial |  |  |  | Customer |  |  | 1.2.1 | I/O Initialization | [13 empty] | 1 | 1 |  |  | 1 | 1 | 1
2008-10-24 | [5 empty] | Customer |  |  | 1.2.1.1 | Initialize pins referenced from ADC Configuration file (Adc_Cfg.c), to enable its ADC mode and take them out from its GPIO mode. |  |  |  | Soft-Low Level Drivers | [9 empty] | 1 | 1 |  |  | 1 | 1 | 1
2008-10-24 | [8 empty] | 1.2.1.2 | Maximum number of ADC channels shall be indicated by a macro named "ADC_MAX_CHANNELS"
2008-10-24 | [5 empty] | Customer |  |  | 1.2.2 | PIT Channel Intialization | [13 empty] | 1 | 1 |  |  |  |  | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.2.2.1 | A PIT channel shall be available to be used as a trigger source to start the conversion of all the ADC Channels configured. * The periodicity of the PIT channel shall be configured by using a macro definition which indicates the time. |  |  |  | Soft-Low Level Drivers |  | One PIT timer shall be available for the PWM implementation | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
2008-10-24 | [5 empty] | Customer |  |  | 1.2.2 | ADC Conversion Rates | [13 empty] | 1 | 1 |  |  |  |  | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.2.2.1 | ADC Channels shall be configured using the convertion rate indicated by their own configuration structure. |  |  |  | Soft-Low Level Drivers |  | One PIT timer shall be available for the PWM implementation | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.3 | ADC Resolution |  |  |  | Soft-Low Level Drivers | [9 empty] | 1 | 1 |  |  | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.2.2.3 | All Channels shall use the resolution conversion indicated by the macro named "ADC_RESOLUTION" |  |  |  | Soft-Low Level Drivers |  | Enough System bus frequency to accomplish with 0.1% period resolution | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.3 | Core Initialization | [13 empty] | 1 | 1 |  |  |  |  | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.3.1 | Initialize which core (Z1 or Z0) shall handle all emios channel interrupts |  |  |  | Soft-Application Functions |  | Z1 core support VLE code | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.4 | ADC Configuration | [13 empty] | 1 | 1 |  |  |  |  | 1
2008-10-24 | [8 empty] | 1.4.1 | Pre-Compile Configuration
2008-10-24 | [5 empty] | Customer |  |  | 1.4.1.1 | ADC Conversion Rates | [13 empty] | 1 | 1 |  |  |  |  | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.4.1.1.1 | ADC Channels shall be configured using the convertion rate indicated by their own configuration structure. |  |  |  | Soft-Low Level Drivers |  | One PIT timer shall be available for the PWM implementation | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.4.1.2 | ADC Resolution |  |  |  | Soft-Low Level Drivers | [9 empty] | 1 | 1 |  |  | 1 | 1 | 1
2008-10-24 | OL | initial | 1 |  |  | Customer |  |  | 1.4.1.2.1 | All Channels shall use the resolution conversion indicated by the macro named "ADC_RESOLUTION" |  |  |  | Soft-Low Level Drivers |  | Enough System bus frequency to accomplish with 0.1% period resolution | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
2008-10-24 | [8 empty] | 1.4.1.3 | ADC Filter Generation
2008-10-24 | [8 empty] | 1.4.1.3.1 | A Macro definition with the naming as follows "ADCx_AVERAGE" shall be defined to let the driver know whether or not to create a Filter buffer for a particular ADC Channel.
2008-10-24 | [8 empty] | 1.4.1.3.2 | Define a macro which indicates the number of ATD0 channels that the software will filter. The value of this macro must be between 1 and the maximum number of channels on ATD0
2008-10-24 | [8 empty] | 1.4.1.3.3 | Defines a macro which let the driver know the number of values to be included in the average calculation.
2008-10-24 | [8 empty] | 1.4.1.3.4 | Define a macro nemaed "ATDx_AVERAGEINTERRUPT" to indicate to the driver whether to generate a software interrupt after all filters have benn calculated. This macro shall be set to "FALSE" if developer doesnt want to generate the interrupt.
2008-10-24 | [8 empty] | 1.4.2 | Runtime Configuration Structure
2008-10-24 | [8 empty] | 1.4.2.1 | A Symbolic name shall describe to which configuration information the ADC module belongs. Example: ADC0 or ADC1
2008-10-24 | [8 empty] | 1.4.2.2 | An average filter shall be available to store the filtering results from an specific ADC module.
2008-10-24 | [8 empty] | 1.4.2.3 | A field shall indicate the ADC driver whether a ADC filtering module is able to start measuring by PIT interrupt mechanism or manually mode.
2008-10-24 | [8 empty] | 1.4.3 | Average Runtime Structure
2008-10-24 | [8 empty] | 1.4.3.1 | A Pointer variable shall be used to store ATD samples
2008-10-24 | [8 empty] | 1.4.3.2 | A Pointer variable to indicate the last sample of a measuring process.
2008-10-24 | [8 empty] | 1.5 | ADC Average Function
2008-10-24 | [8 empty] | 1.5.1 | Alan, could you please indicate what type of requirements needs to average the samples??
2008-10-24 | [8 empty] | 1.6 | ADC Operating Behaviour
[9 empty] | 1.6.1 | The ADC driver shall make useall time the eDMA controller to provide a better performance to the driver and faster response to sampling.
[24 empty] | 1 | 1 |  |  |  |  | 1
[24 empty] | 1 | 1 |  |  |  |  | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 0 | 1
[14 empty] | Soft-Low Level Drivers | [9 empty] | 1 | 1 |  |  | 1 | 1 | 1
[24 empty] | 1 | 1 |  |  |  |  | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 3.1 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[24 empty] | 1 | 1 |  |  | 1 | 1 | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[24 empty] | 1 | 1 |  |  | 1 | 1 | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[24 empty] | 1 | 1 |  |  |  |  | 1
[14 empty] | Soft-High Level Drivers | [9 empty] | 1 | 1 |  |  | 1 | 1 | 1
[14 empty] | Soft-Low Level Drivers | [9 empty] | 1 | 1 |  |  | 1 | 1 | 1
[24 empty] | 1 | 1 |  |  |  |  | 1
[14 empty] | Soft-Application Functions |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[14 empty] | Soft-Low Level Drivers |  | First driver version shall follow most of AutoSAR PWM requirements. Document version 2.1 release 17 | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[24 empty] | 1 | 1 |  |  |  | 1 | 1
[14 empty] | Soft-Operative System | [9 empty] | 1 | 1 |  |  | 1 | 1 | 1
[24 empty] | 1 | 1 |  |  |  | 1 | 1
[14 empty] | Orga-Reports, registers, samples, etc. |  | All functions shall be described in this document without exception. | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[24 empty] | 1 | 1 |  |  |  | 1 | 1
[14 empty] | Soft-Application Functions |  | Sample application shall show at least initialization and configuration functions. | [7 empty] | 1 | 1 |  |  | 1 | 1 | 1
[24 empty] | 1 | 1 |  |  |  | 1 | 1
[14 empty] | Soft-Low Level Drivers | [9 empty] | 1 | 1 |  |  | 1 | 1 | 1
Note on N4: b01252: Blank - Must N - Nice to Have ? - To be defined only for Requirements development, Before approval ? priority must not exist
Note on T4: Technical Solution ID
Note on X4: 1 Requirement is compliance 0 Requirement is not compliance NULL not reviewed

## Test Cases
Test ID | Detailed Explanation | Expected Result

## Fields help
Fields Help on Requirements List
|  | FIELD | Value | Description | Notes | Tips
|  | Capture Date | dd/month/yy | Set the date when the requirement is written | The month name must be written
|  | Capturer | Initials | Set the initials whom captured the requirement
| Requirement control | Req Status | initial | This state is set when the requirement is being captured | The revision number in this state is 0.x
|  |  | approved | The requirement has been approved by the requirement provider | All the requirements has to be approved in order to continue with the Project Plan, and in this moment all the requirements change to Rev 1
|  |  | review | If the requirement has been approved but there is an issue with this one, the requirement status must to be changed to Review Satus, and "Requirement Change Process" is initiated
|  |  | Obosoleted | If there a change in the requirement and the Change has been approved the requirement in review change to Obosoleted and the new requirement is set as approved
|  |  | Deleted | If the requirement is no longer "required" it is stated as Deleted
|  | Req Rev Number | x,x | Revision Number in the format x.x. If the requirement is in the initial state the revision has to be set to 0.x. Once the requirement is approved by customer change to 1.x, any other change must be acomplished of a "Change Control Process"
|  | Rev Date | dd/month/yy | Set the date whe the requirement change is State/Revision
|  | Authorize |  | Set the Name of the person(s) that approve this Requirement
|  | Req Source | Customer
|  |  | TS | Technical Solution Team (derived requirements) | When a requirement ia added by Design, Test, etc.
Test
Legal
Organizational
|  | Req Notes /comments |  | Any note that you consider necessary in order to clarify the motive or state of the requirement only as reference | Fill this field is not mandatory
| Requirement | Req ID | #.#.# | This Field uniquely identifies each requirement, and permits a primary classification of the requirements, the ID is set in a decimal format as 1.1, 2.3.1, etc, with all the levels as required. | If one Requirement Description needs to be modified you don't need to change its Req ID is necessary to set the Requirement Status an Revision accordingly | If you are introducing the Requirement List you can set this Req. ID once that you finished the primary requirement list
|  | Req Description |  | Write the Requirement cleary and properly stated, complete, consitent with other requirements, appropiarte to implement, verifiable(testable) Traceable |  | Use the Requirement CheckList in order to properly state the Requirement
|  | Notes on the requirement |  | This field is only as note it must not be part of the Requirement Description | Fill this field is not mandatory, you must avoid to write parts of the Requirement in this field
| Requirement development | Priority /Quantification |  | This Field is used when you are developing the requirements. This is not required for Requirement Management | This Field is not Mandatory for CMMI Level 2, but is set as tool in the Template
|  |  | Blank | The Requirement must be implemented | Requirement with this field will be implemented
|  |  | Nice to Have | This requirement is nice to have however it require authorization in order to be implemented, a requirement with this priority will not be implemented | a requirement with this priority will not be implemented
|  |  | ? | Requirement To be defined (you have the idea but you are not certainly of it or the Requirement is bad stated this priority is only used in initial state of requirement. This requirement will not be implemented | a requirement with this priority will not be implemented
All of these fields are optional to be filled, and depends on Technical Leader or project necessities | Requirement Classification | Notes on the requirement |  | Technical Leader can use this column for his notes
|  | Priority |  | This Column can have Blank, N, and ? Values | Priority is only used for Requirements Development, before approval must not exist any N or ? Celd
|  | Requirement Clasification |  | Requirements Classification | This Classification will help with WBS developing (planning phase)
|  | Necessity |  | Justification of requirements
|  | Optional 1 |  | These columns are optional according to Technical Leader or project necessities
|  | Optional 2 |  | These columns are optional according to Technical Leader or project necessities
|  | Optional 3 |  | These columns are optional according to Technical Leader or project necessities
|  | Optional 4 |  | These columns are optional according to Technical Leader or project necessities
|  | Optional 5 |  | These columns are optional according to Technical Leader or project necessities
|  | Optional 6 |  | These columns are optional according to Technical Leader or project necessities
|  | Optional 7 |  | These columns are optional according to Technical Leader or project necessities
|  | Value |  | Unit specification of the necessity.
|  | Necessity |  | Necessity description or reference where can be found.
|  | Cost |  | Estimated cost in US dollars of implementing the necessity(30% variation) | This Field is not required for the Requirement Management Process and is set only for compatibility with the previous RTAC template
|  | Other Req. Relationship |  | Input, processing and output with regards to other req. | List all the Req. ID's that have relationship with this requirement | set all the Req ID that are relationship
|  | Assumptions |  | Assumption taken on requirement in order to implemen it
|  | Verification Test |  | Reference where can be found the test procedure. | The Test ID is written in this field and is filled when the Tests are defined
|  | Test Log |  | Code for Tests: 0 = Blank = no performed , 1 = Green = In progress, 2= Red = Pending | This field reflects the Test's Status and is set here only as reference
| Traceability Fields | Test ID |  | Test Identifier (Uniquely number that has reference to each test
|  | Test Description |  | A brief of the Test
|  | TS ID |  | Technical Solution ID
|  | TS Description |  | Technical Solution Description
|  | WBS ID |  | WBS Number description
|  | WBS Description |  | Brief Description of the Planned task
| Requirement Verification Check List | Test case asociated with the requirement |  |  | Note this review is made during meeting reviews, a minute must be taken and you must identify participants, and annotate the requirements reviewed during that Review. Depending on project size or complexity can be several meetings before all requirements has been verified
|  | The requirement can be understood by affected parties (e.g. developers, testers). |  | 1 Requirement is compliance
|  | Requirement contains no TBD. |  | 0 Requirement is not compliance
|  | Unacceptable words and phrases are absent (e.g., adverbs, adjectives, as appropriate, at a minimum). |  | NULL not reviewed
|  | Requirement is at the appropriate level of detail |  |  | Detail must be enough for developers
Requirement is within scope.
Requirement is feasible.
|  | Requirement can be traced to its parent or driver. |  | The Requirement has its ID with appropriate level, i. e. 1.1. -1.1.1.
| Requirement Accomplished date | Requirement Accomplished date |  | Once the requirements has been accomplised you must set the date when you establish that such requirement has been accomplished.
|  | Test Status |  | This filed is optional and allow to use this Requirement Book as Test result tool, Passed, Failed, On-going
|  | Test date |  | Test state date
Configuration Management
|  | projectID_REQB_HL | This file is set under configuration management after repository has been created and High level Requirements have been approved
|  | projectID_REQB_TM | This file is set under configuration management after IPP is signed-off by Customer and Commitment of Stakeholder has been obtained
|  | projectID_REQB_EP | This file is set under configuration management after project is closed (All requirements have been achieved)
Note on C24: b01252: Blank - Must N - Nice to Have ? - To be defined
Note on C29: b01252: Blank - Must N - Nice to Have ? - To be defined only for Requirements development Before approval must not exist any "N" or "?"
Note on C57: 1 Requirement is compliance 0 Requirement is not compliance NULL not reviewed

## Inconsistencies
Project inconsistencies log
Inconsistence No. | Report Date | Reported by | Description | Responsible | Status Date | Status

## Requirement List Example
Control Fields | [8 empty] | Required Fields |  |  | Optional Fields Used for organization and a better understanding of Requirements |  |  |  |  | Traceability Fields | [5 empty] | Requirement check List | [7 empty] | Requirement Accomplished | Test Status
Capture Date | Capturer | Req Status | Req Rev | Rev Date | Authorize | Req Source | Req Notes | CHANGE ID | Req ID | Description / function | Other Req. Relationship | Notes on the requirement | Priority | Requirement Classification | Necessity | Assumptions | Test ID | Test Description | TS ID | TS Description | WBS ID | WBS Description | Test case associated with the requirement | The requirement can be understood by affected parties (e.g. developers, testers). | Requirement contains no TBD. | Unacceptable words and phrases are absent (e.g., adverbs, adjectives, as appropriate, at a minimum). | Requirement is at the appropriate level of detail | Requirement is within scope. | Requirement is feasible. | Requirement can be traced to its parent or driver. | Requirement Accomplished date | Test Status
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1 | BCM for 2 doors | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.1 | 2 window lift system |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.1 | FL window Driver plus |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.2 | FL window Driver minus |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.3 | FR window Driver plus |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.4 | FR window Driver minus |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.5 | FL window UP-switch input |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.6 | FL window Down-switch input |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.7 | FR window UP-switch input |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.8 | FR window Down-switch input |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.1.9 | One- touch for close/open the window (only in front windows) |  |  |  | Soft-Application Functions | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.10 | FL window drive currrent sensor |  |  |  | Hard-Inputs | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.11 | FR window drive currrent sensor |  |  |  | Hard-Inputs | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.12 | Stop current <1A |  |  |  | Soft-Application Functions | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.1.13 | Disable inputs in low consume(VCC wet) |  |  |  | Soft-Application Functions | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-30 | LP | approved | 1 | 2006-08-30 | Customer |  |  |  | 1.1.14 | disable windows (copilot window) |  |  |  | Soft-Application Functions | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.2 | 2 door lock/unlock system | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.2.1 | FL Lock/Unlock Driver plus |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.2.2 | FL Lock/Unlock Driver minus |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.2.3 | FR Lock/Unlock Driver plus |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.2.4 | FR Lock/Unlock Driver minus |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.2.5 | FL Lock switch input |  |  |  | Hard-Output | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.2.6 | FL Unlock switch input |  |  |  | Hard-Inputs | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.2.7 | FR Lock switch input |  |  |  | Hard-Inputs | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.2.8 | FR Unlock switch input |  |  |  | Hard-Inputs | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.2.9 | LOCK_UNLOCK connectors |  |  |  | Hard-User Interfaces | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.3 | wing mirror system (inputs) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.3.1 | select left wing mirror input |  |  |  | Hard-Inputs | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.3.2 | select right wing mirror input |  |  |  | Hard-Inputs | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.3.3 | wing mirror up input |  |  |  | Hard-Inputs | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.3.4 | wing mirror down input |  |  |  | Hard-Inputs | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.3.5 | wing mirror Left input | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.3.6 | wing mirror Right input | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-25 | LP | approved | 1 | 2006-08-25 | Customer |  |  |  | 1.3.7 | Folding mirror command via PC | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.4 | LIN interface |  | It is used to control the wing mirror Left and Right | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.4.1 | Lin_Tx | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.4.2 | lin_Rx | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.4.3 | LIN connector | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.4.5 | LIN messages should be copied into CAN mesagges | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.4.6 | command the wing mirror via LIN | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-29 | LP | approved | 1 | 2006-08-29 | Design |  |  |  | 1.4.7 | LIN_ENABLE | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-29 | LP | approved | 1 | 2006-08-29 | Design |  |  |  | 1.4.8 | LIN WAKE (OPCIONAL) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.5 | CAN interface |  | it is used to communicate with others modules (PC terminal for demo) | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-30 | LP | approved | 2 | 2006-08-18 | Customer |  |  | 2 | 1.5.1 | CAN_RX | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | obsolete | 1 | 2006-08-18 | Customer |  |  | 2 | 1.5.1 | CAN_L | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-30 | LP | approved | 2 | 2006-08-18 | Customer |  |  |  | 1.5.2 | CAN_TX | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.5.2 | CAN_H | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.5.3 | CAN connector TBD | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.5.4 | Protocol definition TBD | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.5.5 | LIN message should be copied into CAN mesagge (only for demo porpuses) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.6 | Turn Key System | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.6.1 | ON - posistion (positive input) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.6.2 | IGN - position (positive input) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.6.3 | START - position (positive input) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.6.4 | OFF Position | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.6.5 | Relay Ignition control (starter driver) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.6.6 | Start –position it block the crank system if is pressed for more than 15 seconds [1i] | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.6.7 | If the system Alarm is Armed the crank signal is blocked | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.7 | Turn Light Control | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.7.1 | Turn Left Light driver | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.7.2 | Turn Right Light Driver | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.7.3 | Turn Left input | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.7.4 | Turn Right Light Input | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.7.5 | When the Alarm System is armed flash one time | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.7.6 | When the Alarm System is Disarmed flash twice | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.7.7 | When the Alarm System is intented to armed and there are opens doors flash three times | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8 | RKE system | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.1 | Echo receiver (based on China's LE BCM) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.2 | RF frequency (433 MHZ) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.3 | ECHO SPI - MOSI | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.4 | ECHO SPI - MISO | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.5 | ECHO SPI - SCK | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.6 | ECHO SPI - SS ? | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.7 | ECHO STROBE control | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.8 | ECHO CONFB | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.9 | RF antenna | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.10 | RSSIOUT (Recieved Signal Strenght Indicator) Analog Output | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.11 | ECHO RSSIC control | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.13 | ECHO Enable _LNA(nice to have) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.14 | ECHO AGC control (nice to have) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.15 | Encryption Algorithm | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.16 | Rolling code Algorithm | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.17 | Strong level connector (analog output) (+ VCC y GND) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.8.18 | Strong level measuring (Echo register) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-29 | LP | approved | 1 | 2006-08-29 | Design |  |  |  | 1.8.19 | ECHO_SEB (opcional) |  | This signal enable the digital system | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.9 | security | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.9.1 | External WDT atention | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.9.2 | LVI | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.9.3 | COP | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.9.4 | TVS transition voltage suppresor | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.9.5 | Flash protection bits | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.10 | miscellaneous | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.10.1 | Battery voltage measuring | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.10.2 | VCC wet Control | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.10.3 | Trunk ajar Driver | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.10.4 | REMOVED Hood ajar Driver | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.10.5 | Info LED | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.10.6 | Demo MODE (to receive the locks and windows switches form PC) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.10.7 | SWITCH_SS (multiple switch slave select) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.10.8 | SBC_CAN_CS (SS2 for SPI device) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.11 | Dome Light | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.11.1 | Dome Light Drive PWM output | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.11.2 | Dome Light Switch ON - OFF - AUTO | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.11.3 | When the door is opened, dimming - on | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.11.4 | When the door is close, delay, dimming - off | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.11.5 | If the Alarm System is Armed (dimming - off without delay) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.11.6 | If the Alarm System is Disarmed (dimming - On) if the any door is not open during the next 30sec the ligth turn off | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.12 | Alarm System | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.12.1 | FL Door switch input | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.12.2 | FR Door switch input | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.12.3 | Trunk Open switch input | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.12.4 | Hood Open switch input | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.12.5 | Burglar Alarm Feedback LED | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.12.6 | If you want to Arm the Alarm System, and there are some door open, the siren beeps 3 times and the Alarm system is not Armed | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.12.7 | If the car is closed the Alarm System is Armed automatically after 60sec | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.12.8 | If the siren is ON it will be OFF 10 minutes after (In mode Demo this time is set to 60 sec) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-14 | LP | approved | 1 | 2006-08-14 | Customer |  |  |  | 1.12.9 | BA LED connector | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-29 | LP | approved | 1 | 2006-08-29 | Customer |  | No previously listed (already included on Block Diagram) | 6 | 1.12.10 | Siren Output | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.13 | Power Supply | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.13.1 | System Supply 7 a 18 Vcd (car system) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.13.2 | 5Vcd microcontroller supply | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.14 | Audible Feedback |  | (nice to have) | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.14.1 | Internal Buzzer OUTPUT (PWM) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.14.2 | The Internal buzzer sounds when the key is on ON-position and the driver's door is open | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.15 | BDM |  | connector for debug and programing | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 1.15.1 | BDM connector | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-14 | LP | approved | 1 | 2006-08-14 | Customer |  |  |  | 1.16 | Headlights | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-14 | LP | approved | 1 | 2006-08-14 | Customer |  |  |  | 1.16.1 | High beam output | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-14 | LP | approved | 1 | 2006-08-14 | Customer |  |  |  | 1.16.2 | Low beam output | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-14 | LP | approved | 1 | 2006-08-14 | Customer |  |  |  | 1.16.3 | High beam switch input | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-14 | LP | approved | 1 | 2006-08-14 | Customer |  |  |  | 1.16.4 | Low beam switch input | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-14 | LP | approved | 1 | 2006-08-14 | Customer |  |  |  | 1.16.5 | If the Alarm System become armed and the headlights are on, the BCM will turn off the headlights after one time delay | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-29 | LP | approved | 1 | 2006-08-29 | TS |  |  |  | 1.17 | Emulated SPI |  | This SPI is required in order to have an independient SPI for SBC-CAN and Multiple Switch | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.17.1 | E_SCK | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.17.2 | E_MOSI | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| LP | approved | 1 | 2006-08-18 | TS |  |  |  | 1.17.3 | E_MISO | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-30 | LP | approved | 1 | 2006-08-30 | TS |  |  |  | 1.17.4 | Interruption pin from Multiple switch detection | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-30 | LP | approved | 1 | 2006-08-30 | TS |  |  |  | 1.17.5 | SBC_CAN_INT |  | This signal notify ti microcontroller if ther any issue with this chip | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 2 | Wing Mirror with LIN Interface | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 2.1 | wing mirror protocol |  | This protocol is determinated by Ken Andersen | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 3 | Key Fob | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 3.1 | QG8 microcontroller | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 3.2 | TANGO trasnmiter | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 3.3 | Low power consume mode | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 3.4 | KEY FOB commercial case type | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 3.5 | Button 1 Unlock |  | Open door locks, siren beep twice, turn lights ligths twice, dimmin -on | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 3.6 | Button 2 Lock |  | Close windows, locks doors, siren beep once, turn lights light once, dimming - off | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 3.7 | Button 3 Panic |  | If pressed for more than 3 sec Siren is triggered | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 3.8 | Button 4 Trunk |  | Trunk ajar | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 3.9 | Batteries operated? 20mm |  | Type TBD | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 3.10 | Button pressed fimerly |  | Open windows | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 3.11 | encryption algortihm | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 3.12 | rolling code algorithm | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4 | PC Terminal | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.1 | windows lift simulation Right Door | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.2 | lonk/unlock position simulation (the BCM requires a DEMO mode ) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.3 | USB- CAN protocol | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.4 | Speed simulation to send the information via CAN | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.5 | Echo Receiver strong signal level shown in screen (Nice to Have) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.6 | CAN protocol summary screen | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.7 | LIN protocol summary screen (mesagges send via CAN) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.8 | Open/Close Door status (2 doors, hood and trunk) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.9 | Open/close Door simulation (BCM in DEMO Mode) |  | click on the door to OPEN/CLOSE | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.10 | Lock/unlock switch control simulation for right Door |  | click on switch to LOCK/UNLOCK | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.11 | Right Wing mirrror simulation moved by the Key PAD (position UP, DOWN, RIGHT, LEFT) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.12 | Installation Software | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 4.13 | User guide | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 5 | CAN-USB converter | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | TS |  |  |  | 5.1 | Get on USB- CAN converter (buy) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6 | Door Scale Module | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.1 | Portable (equal or less than 60 x 70 cm) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.2 | Case must be considerated (holders and wheels) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.3 | Expo presentation (quality finished) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.4 | Professional Wiring (Wiring diagram, wire ties, wire wraps, harnesses, labels) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.5 | Easy to set up | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6 | Key Pad on driver's side (Automotive) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.1 | Lock/Unlock switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.2 | Lock/Unlock or Windows disable switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.3 | FL window Up switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.4 | FL window Down switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.5 | FR window Up switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.6 | FR window Down switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.11 | Left wing mirror select switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.12 | Right wing mirror select switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.13 | wing mirror up switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.14 | wing mirror down switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.15 | wing mirror left switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.6.16 | wing mirror right switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.7 | FL Window lift system (Automotive) |  | This system is adapted for the Scale Module | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.8 | FL Lock/unlock system (automotive) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.9 | Turn Key Switch (Automotive) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.10 | Dome Light (Automotive) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.11 | Turn Ligths (Right and Left) (Automotive or LED) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.12 | Left wing mirror (Automotive) with LIN connector | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.13 | Dome Light Switch (ON - OFF - AUTO) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.14 | FL Door switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.15 | Trunk ajar switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.16 | Hood ajar switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.17 | Trunk ajar output (solenoid or LED ) |  | selenoid or LED TBF | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.18 | Hood ajar output (LED type) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.19 | Siren (Buzzer Type) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.20 | BA-Light (LED) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.21 | Power Supply (12V @ 15A) |  | PC power supply | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.22 | The Laptop space in front of the Scale Door Model must be cosiderated | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.23 | Window to show the BCM PCB |  | This window permits to see the PCB | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.24 | CAN connector for converter CAN/USB |  | DB9 Female | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.25 | Power connector (Vca) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.26 | Windows Level (Nice to have) for FL window | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.27 | ECHO received strong level indicator (Nice to Have) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.28 | Window strong enough to show Anti pinch Algorithm (Nice to Have) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 6.29 | Lock/unlock outputs for FR, RL; RR (LED) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-14 | LP | approved | 1 | 2006-08-14 | Customer |  |  |  | 6.30 | Headlight switch High beam | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-14 | LP | approved | 1 | 2006-08-14 | Customer |  |  |  | 6.31 | Headlight switch Low beam | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-31 | LP | approved | 1 | 2006-08-31 | Customer |  | This function was include by Customer requirement (on the 2nd pass revision) |  | 6.32 | Turn Left/Rigth Switch | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-31 | LP | approved | 1 | 2006-08-31 | Design |  | In order to show the external LIN mirror |  | 6.33 | LIN Connector | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-31 | LP | initial | 1 | 2006-08-31 | Customer |  | It should be considered |  | 6.34 | High Beam LED | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-31 | LP | approved | 1 | 2006-08-31 | Customer |  | It should be considered |  | 6.35 | Low Beam LED | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-31 | LP | initial | 1 | 2006-08-31 | Design |  |  |  | 6.36 | Buzzer signals | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 7 | Documentation | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 7.1 | One pager for Scale Door Module | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 7.2 | Reference Design for BCM with DZ60 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 7.3 | Hand out one pager for all FSL ICS used | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 7.3.1 | DZ60 -CAN | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 7.3.2 | ECHO (Encryption rolling codes) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 7.3.3 | SBC? | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 7.3.4 | TANGO- QG8 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 7.4 | PC terminal User's Manual | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 7.5 | Packing List | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2006-08-11 | LP | approved | 1 | 2006-08-18 | Customer |  |  |  | 7.6 | Exportation letter | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Note on N4: b01252: Blank - Must N - Nice to Have ? - To be defined only for Requirements development, Before approval ? priority must not exist
Note on T4: Technical Solution ID
Note on X4: 1 Requirement is compliance 0 Requirement is not compliance NULL not reviewed